Notes of meeting held on 17th June 2010 at 11:30 am

London Councils

Presentations available:

http://www.londoncouncils.gov.uk/London%20Councils/LCIPProgressJune2010.pdf

http://www.londoncouncils.gov.uk/policylobbying/culturetourismand2012/lcip/data.htm

| Attending: Christine Parsloe (Chair, LB Merton), Sue Thiedeman (CSIM), Tina Morton (MLA/LCIP), Tony Leach (London Parks & Green Spaces Forum), Veronica Howe (LCIP), Francis McParland (LB Merton), Joel Brookfield (SE London), Sarah Murray (LCIP), Lorraine Lynch (LB Lambeth), Chris Ruse (LB Wandsworth), Richard Sved (MLA), Samantha Coates (EH), Carl Cheevers (LB Croydon), Stefania Horne (LB Redbridge), Carol Boswarthack (City), Despina Kyprianou (LB Camden), Cate Canniffe (ACE), Alexandra Rook (London Parks & Greenspaces Forum), Simon Gardener (LB Enfield), Michael Sterry (Lee Valley Regional Park), Catherine Hillis (London Councils), Tim Douglas (LB Hounslow), Howard Simmons (Audit Commission), David Ruse (LB Westminster) |
| --- |
| Key issues raised | Action |
| 1. Welcome and Introductions Christine Parsloe |  |
| 2. Minutes of last meeting (1 March 10) and matters arising Christine Parsloe 2. London Parks Forum members event postponed until 8 October Venue London’s Living Room 3. ST reported that MSO tranche 3 better attended and higher percentage of Heads of Services attending 3.b. CSIT analysis some more documents have been submitted Some boroughs reluctant as members/senior managers are nervous | ALL to ensure that bullet points of key improvements have been submitted as minimum |
| 3. London Cultural Improvement Programme – update Sue Theideman/Tina Morton London Cultural Improvement Programme Sue Thiedeman Report complete and published Action Planning to commence Needs to link to CASE Review IDeA emerging Outcomes Framework Rapidly changing landscape Community of practice being established for Performance Managers DISCUSSION: unknown budget issues; some new investment as part of renegotiated leisure contracts; very rapidly changing picture; strategic partnerships a strength, some borough facing 15-20% year on year cuts, opportunities - culture has story to tell esp. around volunteering Data review: GREEN Report complete and published Action Planning to commence Needs to link to CASE Review IDeA emerging Outcomes Framework Rapidly changing landscape Community of practice being established for Performance Managers Impact and outcome measures: GREEN Tranche 3 underway 17 Boroughs taken part Range of programmes Range of levels and sectors engaged Webtools now developed and available Community of Practice launched CSIT/Peer Lead Challenge: GREEN Self Assessments and peer challenges almost complete Still need to receive some paperwork to strengthen analysis and evidence Further theme under development by IDeA Currently at pilot stage Museum Improvement programme: GREEN Museums Improvement Network well established and programme of support continuing All self assessments and peer challenges complete Tranche 2 improvement projects being delivered Phase 3 under development Potentially £70K to support transformation agenda Advocacy: GREEN Impact of political change in London and London Councils Member briefings and inductions Some planned events are postponed Considering bespoke event Need new champion for Liberal group Utilising existing events E.g. Mayor’s cultural strategy consultation 29 July Future of Cultural Services 29 July Library Change Programme: GREEN London Councils will host new Director post shortly to be advertised Survey on best practice imminent to kick off the best practice elements 1 July seminar NSA COP being set up for London COP for all regions undertaking similar work established Working with Children’s Services: GREEN Director of Children's Services nominated by ALDCS – Gillian Palmer, LB Greenwich Case studies to be published July 2010 17 Borough Champions identified and inception meetings taking place Training delivered ; Safeguarding; Makaton; LAA Mapping of existing training Arts education questionnaire Heritage Change Programme: AMBER Draft Tender Brief Developed Stakeholder workshop held 11 June 10 Project will focus on supporting LA’s with transformation agenda Mapping Engagement Options appraisal DR: offered input as is involved in TNA National Strategy roll out London Events Network and Training: GREEN Needs analysis/mapping project Interim report presented Planning meeting for peer to peer mentoring Bespoke booking software brief developed Events toolkit brief developed and advertised Marketing Culture for the Visitor Economy: GREEN 3 successful marketing workshops oversubscribed, plus additional bespoke session for sports Detailed seminars run on topics arising from marketing workshops: Digital Marketing, Perfect PR & Targeted marketing – really successful project Online guides to be published in late summer 2010 Improving Fundraising Capability: AMBER Need to ensure that this piece of work is reframed so that it is relevant for the current financial situation FilmApp: GREEN 9 boroughs signed up for initial roll out Further 4 expressed an interest System coming to end of development stage being rolled out in first 2 boroughs Survey to gather baseline evidence from borough film offices and location managers underway System builds in KPIs Project Management: RED Programme team posts secure to March 2011 Funding gap still exists Need for posts and project will need to be reviewed nearer to 2011 English Heritage contribution confirmed; additional £5K from IDeA for MSO work MLA & ACE funding increased for 2010-11 Potential join up with London Living Places Partnership a) Demonstration – MSO Webtools Sarah Murray http://lcipmso.weebly.com Being used by East and East Midlands. b)London Data Access Review Tina Morton http://www.londoncouncils.gov.uk/networks/lcip/data.htm Discussion: importance of data; lack of impact where it is missing; need to be more proactive as data often out of date; CASE and modelling work; useful to drive up service delivery and improvement; funding sources, data for business planning and measurement; need for smarter action plan and shared KPIs. Volunteers sort for action planning group. Look at data already collected, highlight half a dozen and agree collection method. Shaping the Fundraising study Christine Parsloe Discussion: Agreed work needs to be done, looking at best practice and cross council /cross service working. Big Society has implications for funding, skills and capacity. Needs to be practical. Not just fundraising need to look at invest to save, philanthropy and income generation. | Need a new Lib Dem member champion – suggestions welcome All to check if borough has nominated a champion ST to provide COs with crib sheet of LCIP success & evidence SM to circulate list of those who attended training for boroughs TM/SM to send out link to MSO web tools ST to resend invitation to COP |
| 4. Bids for London Council Research Budget Catherine Hillis Agreed Catherine’s proposals are sound and timely. Need to include global best practice e.g. Paris, New York, Canada etc. |  |
| 5. New CSIT Theme – Efficiency / VFM Sue Thiedeman Further theme under development by IDeA Currently at pilot stage |  |
| 6.Developing Performance Framework for Culture Sue Thiedeman IDeA emerging Outcomes Framework – soon to be out for consultation |  |
| 7. AOB |  |
| Dates of the next meetings: 29 September “The Future of Cultural Services” Conference, London’s Living Rooms GLA 7 December London Councils | ST CH |