## CSP violence ACTION PLAN
NAME OF BOROUGH - Community Safety Partnership Local Violence and Vulnerability Reduction Action Plan
2021/22 |  | Name | Organisation |  | Role |  |  |  |  | Key Local Strategic Documents that support violence reduction
CSP Chair
ACTION PLAN |  |  | Local Authority |  | Chief Executive
|  |  | Local Authority |  | Local Authority Leader/Mayor
|  |  | MPS |  | BCU Commander
SENIOR |  |  | Local Authority |  | Director of Children's Services
|  |  | Local Authority |  | Director of Public Health
LEADERSHIP |  |  | Local Authority |  | Director/Head of Community Safety
|  |  | London Fire Brigade |  | Borough Commander London Fire Brigade
|  |  | Probation Service |  | Area service lead officer
|  |  | Local Authority |  | Local Authority Housing Director
|  |  | Local Authority |  | Lead Member for Community Safety
|  |  | Local Authority |  | Lead Member for Children's Services
|  |  | Victims Support |  | Local Senior Operations Manager
|  |  | Safer Neighbourhood Board |  | Chair
|  |  | Clinical Commissioning Group |  | Partnership lead
|  |  | Early Help & Prevention |  | Head of Service
|  |  | Community Voluntary Sector |  | Chief Executive/Partnership lead
Ref | [5 empty] | Actions | [5 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
GOVERNANCE | 1 | Set out the local co-ordination arrangements between the Community Safety Partnership, Local Safeguarding Children Partnerships and Safeguarding Adults Boards and the Health and Wellbeing Board, to support a public health approach to reduce violence
| 2 | CSP Meeting agendas to include Violence Performance, consideration of repeat knife carriers, community tensions and stop and search as standing items
| 3 | Implement daily violence assessment meeting attended by police BCU, relevant Local Authority colleagues and Probation
| 4 | Monthly Tactical Tasking Co-ordination Group (or local equivalent) to include Violence Intelligence Briefing, tasking of partnership services to target offenders and hotspot locations; maintain and or review Events Tracker to identify and manage events of risk, monitor and review community tensions and community feedback
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
ANALYSIS & ENFORCEMENT | 1 | Analysis to support a public health approach to violence reduction - including a Strategic Needs Assessment to understand patterns of violence and vulnerability, key local drivers, contexts where harm is occurring and communities/localities of greatest need, as well as a gap analysis against existing evidence of effective practice to inform the local action plan. The Community Safety Strategic Assessment to include serious youth violence, knife and gun enabled crime (to be refreshed annually)
| 2 | Use ISTV and wider public health data, social media intelligence, local drugs markets and local rescue and response county lines analysis, plus any other relevant local authority data i.e. Children social care, sources to inform the strategic assessment analysis and partnership tactical delivery
| 3 | Police tactical plan to be maintained to record, monitor and review key police tactical interventions and activity in support of the Violent Crime Task Force and local Violence Suppression Unit. • If using 4P's the different elements to read across into this partnership plan • MPS hotspot analysis to be shared with partners and subject of further analysis to support bespoke interventions • Problem Orientated Policing to be undertaken in key identified hotspots, collaborating with local authorities, housing providers, landowners, businesses and residents • Disruption of gangs to have SRO/LRO for each BCU and have partnership input and analysis as required
| 4 | Multi-Agency Panel response to those at risk of or involved in violence, as well as tracking and planning responses to locations of risk and harm, including Police, Community Safety, Adult's and Children's Services, YOT,Probation. Meeting minimum of monthly with TOR and menu of options to manage risk through enforcement, prevention and diversion activities. This could be a single meeting, or seperate meetings for those involved in violence and those flagged as at risk and high harm and who could benefit from preventative support.
| 5 | Compile a gangs problem profile for the borough, taking appropriate account of county lines. To be reviewed in-depth every three years and refreshed every 12 months
| 6 | Analysis of the needs and risks of young women involved in violence to be able to develop appropriate interventions for young women
| 7 | Training for front line staff, including partner agencies, on information sharing specific to violence and vulnerbilities so they are confident of what data can be shared and how. Where appropriate drawing on the ICO gangs checklist https://ico.org.uk/for-organisations/in-your-sector/police-justice/processing-gangs-information-a-checklist-for-police-forces/
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
REDUCING ACCESS TO WEAPONS | 1 | Develop an agreed joint programme of actions to remove weapons and provide reassurance including Trading Standards initiatives (e.g. knife or corrosive substance test purchases)
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
SAFEGUARDING AND EDUCATING CHILDREN AND YOUNG PEOPLE Recognising the importance of safeguarding and working alongside places of education | 1 | Work to ensure education settings are safe inclusive places to learn, that build young people’s resilience and have a trauma informed approach, and Children and young people have safe spaces/routes for them to speak to teachers around any concerns reated to violence and vulnerbilites.
| 2 | Schools to include youth violence within their safeguarding plans as per Safeguarding children and young people in education from knife crime (2019) Ofsted guidance
| 3 | Demonstrable partnership work to minimise school exclusions (and managed moves in place of exclusions), create inclusive settings and support young people back into education, employment and training, with schools and academies exclusions policy reflecting the practice set out in DfE statutory guidance
| 4 | Monitor exclusions data, including any patterns around high rate of disproportionality, through local education arrangements and local authority, alongside partners, with clear processes and evidence of challenge where data or practice indicate exclusions do not align with statutory guidance.
| 5 | Due care and attention to corporate parenting principles, and ensure support to children in care and care leavers, through diversion and preventative work that is bespoke to the risk of them becoming involved in serious violence
| 6 | Work with parents and carers, especially those deemed to be vulnerable, to effectively engage young people in diversionary activities and education and prevent harm, using a culturally competent trauma informed approach.
| 7 | Universal and targeted evidence-based programmes delivered across schools, including as part of PSHE offer (new SRE curriculum frrom September 2020), based on local safeguarding issues and trends, with mechanisms in place for partners within borough and across London to support schools to assess quality and impact,
| 8 | Named Safer Schools Officer available to every school in the borough and actively engaged by schools within day to day safeguarding activity.
| 9 | Bespoke support for students in PRU's/AP, including mentoring and transition back into mainstream education or on to further education, training, employment (e.g VRU PRU mentoring scheme)
| 10 | Work to ensure locations such as parks, shopping centres, fast food outlets etc are safe places for children and young people.
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
WORKING WITH COMMUNITIES AND NEIGHBOURHOODS TO REDUCE VIOLENCE | 1 | CSP to work with communities to reduce violence, including young people and the VCS, with appropriate programmes of community involvement, capacity building and regular engagement
| 2 | Community Tensions Monitoring - Community Impact Assessment by MPS to be shared with and informed by CSP partners so it is based on multi-agency data
| 3 | Facilitate community involvement in Stop & Search - including the monitoring of S60 by community representatives. This action should set out what the local arrangements are.
| 4 | Develop a local partnership response to serious violence critical incidents, making use of the VRU CSP Serious Incident Toolkit where appropriate. Consider applying to the VRU critical incident fund, for a small one off funding grant to directly support communities in the aftermath of a serious incident of violence.
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
SUPPORTING VICTIMS OF VIOLENCE AND VULNERABILITY Ensuring co-ordinated referral and support to victims and those who are vulnerable | 1 | To have a multi-agency assessment and referral process through a Multi-Agency Safeguarding Hub or similar, with full partner sign-off of terms of reference and operating model.Local Safeguarding partners to ensure robust and relevant social care oversight for young people at risk of harm.
| 2 | All young victims of violence and those vulnerable to exploitation, are referred to appropriate packages of support across both statutory and voluntary provision. This could include to the London Victim and Witnesses Service which supports victims and witnesses of crime in London to cope and recover from their experiences.
| 3 | Young victims of violence to have a trauma informed needs assessment, with referral to the Your Choice CBT programme or CAHMS where the assessment determines that to be appropriate
| 4 | London Trauma and A&E centres to provide safeguarding information to local partnerships through an agreed referral mechanism and hence maximise opportunities for "teachable moments" and rapid service referral/support
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
POSITIVE DIVERSION FROM VIOLENCE Recognising that children and young people should be offered interventions which help them move away from criminality | 1 | Pre-court and post conviction violent crime offenders to be provided with bespoke community sentence interventions
| 2 | Develop a local schedule of intervention options taking account of available services, including these in the VRU Diversion Directory. Include referral to the Your Choice CBT programme, where that is an appropriate option
| 3 | Use the MPS DIVERT programme to support referrals from police custody to local providers to support education, employment, training (will be rolled out to all BCUS in 2021).
| 4 | Use the new London IOM framework, which focuses partner agencies on persistent, violent offenders who pose at least a medium risk of violent reoffending as the core/fixed IOM cohort, to proactively manage local, priority offender and make best use of shared IOM resources and share information.
| 5 | Probation Service bespoke license conditions for violent offenders should include opportunities for training, employment, education and housing and to complete interventions within the new probation model specifically related to reducing the risk of violence, weapon offending and improved personal well-being.

## Sheet1
NAME OF BOROUGH - Community Safety Partnership Local Violence and Vulnerability Reduction Action Plan
2021/22 |  | Name | Organisation |  | Role |  |  |  |  | Key Local Strategic Documents that support violence reduction
CSP Chair
ACTION PLAN |  |  | Local Authority |  | Chief Executive
|  |  | Local Authority |  | Local Authority Leader/Mayor
|  |  | MPS |  | BCU Commander
SENIOR |  |  | Local Authority |  | Director of Children's Services
|  |  | Local Authority |  | Director of Public Health
LEADERSHIP |  |  | Local Authority |  | Director/Head of Community Safety
|  |  | London Fire Brigade |  | Borough Commander London Fire Brigade
|  |  | Probation Service |  | Area service lead officer
|  |  | Local Authority |  | Local Authority Housing Director
|  |  | Local Authority |  | Lead Member for Community Safety
|  |  | Local Authority |  | Lead Member for Children's Services
|  |  | Victims Support |  | Local Senior Operations Manager
|  |  | Safer Neighbourhood Board |  | Chair
|  |  | Clinical Commissioning Group |  | Partnership lead
|  |  | Early Help & Prevention |  | Head of Service
|  |  | Community Voluntary Sector |  | Chief Executive/Partnership lead
Ref | [5 empty] | Actions | [5 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
GOVERNANCE | 1 | Set out the local co-ordination arrangements between the Community Safety Partnership, Local Safeguarding Children Partnerships and Safeguarding Adults Boards and the Health and Wellbeing Board, to support a public health approach to reduce violence
| 2 | CSP Meeting agendas to include Violence Performance, consideration of repeat knife carriers, community tensions and stop and search as standing items
| 3 | Implement daily violence assessment meeting attended by police BCU, relevant Local Authority colleagues and Probation
| 4 | Monthly Tactical Tasking Co-ordination Group (or local equivalent) to include Violence Intelligence Briefing, tasking of partnership services to target offenders and hotspot locations; maintain and or review Events Tracker to identify and manage events of risk, monitor and review community tensions and community feedback
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
ANALYSIS & ENFORCEMENT | 1 | Analysis to support a public health approach to violence reduction - including a Strategic Needs Assessment to understand patterns of violence and vulnerability, key local drivers, contexts where harm is occurring and communities/localities of greatest need, as well as a gap analysis against existing evidence of effective practice to inform the local action plan. The Community Safety Strategic Assessment to include serious youth violence, knife and gun enabled crime (to be refreshed annually)
| 2 | Use ISTV and wider public health data, social media intelligence, local drugs markets and local rescue and response county lines analysis, plus any other relevant local authority data i.e. Children social care, sources to inform the strategic assessment analysis and partnership tactical delivery
| 3 | Police tactical plan to be maintained to record, monitor and review key police tactical interventions and activity in support of the Violent Crime Task Force and local Violence Suppression Unit. • If using 4P's the different elements to read across into this partnership plan • MPS hotspot analysis to be shared with partners and subject of further analysis to support bespoke interventions • Problem Orientated Policing to be undertaken in key identified hotspots, collaborating with local authorities, housing providers, landowners, businesses and residents • Disruption of gangs to have SRO/LRO for each BCU and have partnership input and analysis as required
| 4 | Multi-Agency Panel response to those at risk of or involved in violence, as well as tracking and planning responses to locations of risk and harm, including Police, Community Safety, Adult's and Children's Services, YOT,Probation. Meeting minimum of monthly with TOR and menu of options to manage risk through enforcement, prevention and diversion activities. This could be a single meeting, or seperate meetings for those involved in violence and those flagged as at risk and high harm and who could benefit from preventative support.
| 5 | Compile a gangs problem profile for the borough, taking appropriate account of county lines. To be reviewed in-depth every three years and refreshed every 12 months
| 6 | Analysis of the needs and risks of young women involved in violence to be able to develop appropriate interventions for young women
| 7 | Training for front line staff, including partner agencies, on information sharing specific to violence and vulnerbilities so they are confident of what data can be shared and how. Where appropriate drawing on the ICO gangs checklist https://ico.org.uk/for-organisations/in-your-sector/police-justice/processing-gangs-information-a-checklist-for-police-forces/
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
REDUCING ACCESS TO WEAPONS | 1 | Develop an agreed joint programme of actions to remove weapons and provide reassurance including Trading Standards initiatives (e.g. knife or corrosive substance test purchases)
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
SAFEGUARDING AND EDUCATING CHILDREN AND YOUNG PEOPLE Recognising the importance of safeguarding and working alongside places of education | 1 | Work to ensure education settings are safe inclusive places to learn, that build young people’s resilience and have a trauma informed approach, and Children and young people have safe spaces/routes for them to speak to teachers around any concerns reated to violence and vulnerbilites.
| 2 | Schools to include youth violence within their safeguarding plans as per Safeguarding children and young people in education from knife crime (2019) Ofsted guidance
| 3 | Demonstrable partnership work to minimise school exclusions (and managed moves in place of exclusions), create inclusive settings and support young people back into education, employment and training, with schools and academies exclusions policy reflecting the practice set out in DfE statutory guidance
| 4 | Monitor exclusions data, including any patterns around high rate of disproportionality, through local education arrangements and local authority, alongside partners, with clear processes and evidence of challenge where data or practice indicate exclusions do not align with statutory guidance.
| 5 | Due care and attention to corporate parenting principles, and ensure support to children in care and care leavers, through diversion and preventative work that is bespoke to the risk of them becoming involved in serious violence
| 6 | Work with parents and carers, especially those deemed to be vulnerable, to effectively engage young people in diversionary activities and education and prevent harm, using a culturally competent trauma informed approach.
| 7 | Universal and targeted evidence-based programmes delivered across schools, including as part of PSHE offer (new SRE curriculum frrom September 2020), based on local safeguarding issues and trends, with mechanisms in place for partners within borough and across London to support schools to assess quality and impact,
| 8 | Named Safer Schools Officer available to every school in the borough and actively engaged by schools within day to day safeguarding activity.
| 9 | Bespoke support for students in PRU's/AP, including mentoring and transition back into mainstream education or on to further education, training, employment (e.g VRU PRU mentoring scheme)
| 10 | Work to ensure locations such as parks, shopping centres, fast food outlets etc are safe places for children and young people.
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
WORKING WITH COMMUNITIES AND NEIGHBOURHOODS TO REDUCE VIOLENCE | 1 | CSP to work with communities to reduce violence, including young people and the VCS, with appropriate programmes of community involvement, capacity building and regular engagement
| 2 | Community Tensions Monitoring - Community Impact Assessment by MPS to be shared with and informed by CSP partners so it is based on multi-agency data
| 3 | Facilitate community involvement in Stop & Search - including the monitoring of S60 by community representatives. This action should set out what the local arrangements are.
| 4 | Develop a local partnership response to serious violence critical incidents, making use of the VRU CSP Serious Incident Toolkit where appropriate. Consider applying to the VRU critical incident fund, for a small one off funding grant to directly support communities in the aftermath of a serious incident of violence.
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
SUPPORTING VICTIMS OF VIOLENCE AND VULNERABILITY Ensuring co-ordinated referral and support to victims and those who are vulnerable | 1 | To have a multi-agency assessment and referral process through a Multi-Agency Safeguarding Hub or similar, with full partner sign-off of terms of reference and operating model.Local Safeguarding partners to ensure robust and relevant social care oversight for young people at risk of harm.
| 2 | All young victims of violence and those vulnerable to exploitation, are referred to appropriate packages of support across both statutory and voluntary provision. This could include to the London Victim and Witnesses Service which supports victims and witnesses of crime in London to cope and recover from their experiences.
| 3 | Young victims of violence to have a trauma informed needs assessment, with referral to the Your Choice CBT programme or CAHMS where the assessment determines that to be appropriate
| 4 | London Trauma and A&E centres to provide safeguarding information to local partnerships through an agreed referral mechanism and hence maximise opportunities for "teachable moments" and rapid service referral/support
Ref |  | Actions | [9 empty] | Risk
Theme | Action No | Actions | Outcomes | Named CSP Lead | Lead organisation | Start date | End date | Supporting organisation(s) | Progress | Comment | Document Reference(s) | RAG status
POSITIVE DIVERSION FROM VIOLENCE Recognising that children and young people should be offered interventions which help them move away from criminality | 1 | Pre-court and post conviction violent crime offenders to be provided with bespoke community sentence interventions
| 2 | Develop a local schedule of intervention options taking account of available services, including these in the VRU Diversion Directory. Include referral to the Your Choice CBT programme, where that is an appropriate option
| 3 | Use the MPS DIVERT programme to support referrals from police custody to local providers to support education, employment, training (will be rolled out to all BCUS in 2021).
| 4 | Use the new London IOM framework, which focuses partner agencies on persistent, violent offenders who pose at least a medium risk of violent reoffending as the core/fixed IOM cohort, to proactively manage local, priority offender and make best use of shared IOM resources and share information.
| 5 | Probation Service bespoke license conditions for violent offenders should include opportunities for training, employment, education and housing and to complete interventions within the new probation model specifically related to reducing the risk of violence, weapon offending and improved personal well-being.

## MENU OF OPTIONAL ACTIONS
Theme |  | MENU OF OPTIONAL ACTIONS TO ADD TO THE ACTION PLAN
GOVERNANCE | 1 | Hold an annual Local Leadership event (Elected members, Statutory Officers, CVS and local Businesses) to look at 'wicked issues' to ensure multi-agency response, e.g. Building community trust in statutory services.
ANALYSIS & ENFORCEMENT | 1 | Use of intelligence led Stop and Search including use of S60 in accordance with NPCC guidance. Inteligence can be fed into the Violence Supression Units to action.
| 2 | Local Authority enforcment through use of all enforcement assets to target locations and offenders, for example CCTV, Enforcement Officers, Parking Enforcement, removal of abandoned vehicles
| 3 | Conduct analysis to understand the disproportionate impact of violence within local communities and groups
| 4 | Licensing - If a specific venue is identified as being associated with an incident(s) of violence, and it is Licensed (For example a Pub, Nightclub, Betting Shop, etc), seek to contact & utlise the expertise of Local Council & Police Licensing Teams in order to mitigate this risk. These teams can offer a range of partnership & enforcement options in order to improve safety at the venue and reduce said violence. (Potential Enforcement Options include – Review of Licence, Emergency Closure Powers and prosecutions under the Licensing or Gambling Act).
REDUCING ACCESS TO WEAPONS | 1 | Local process where weapons can be safely disposed of, without repurcussions such as knife amnesties or knife bins
| 2 | Conduct weapon sweeps such as Community Weapon Sweeps, or sweeps by staff or partners agencies e.g LFB, housing providers/estate managers, refuse collectors
| 3 | Responsible retailer agreements- https://nbcc.police.uk/guidance/knife-retailers-toolkit
| 4 | Physical improvements of localities to design out opportunities to store weapons
| 5 | Target Hardening of retailers to prevent shoplifting
| 6 | Work collaboratively with local authority trading standards teams and conduct U18 and Challenge25 Test Purchase operations.
| 7 | Partnerships to acces the Police Youth and Community Centre Safety Scheme. Phase 2 applications were opened to all BCUs/boroughs.
SAFEGUARDING AND EDUCATING CHILDREN AND YOUNG PEOPLE | 1 | Intelligence sharing and tension monitoring between education establishments and local authority through named safer schools officers
| 2 | MPS Youth Problem Solvers (PCs) providing support towards a preventative approach in serious youth violence reduction in 10 priority boroughs. This is reviewed on a quarterly basis, thus ensuring the right boroughs get the right help.
| 3 | Promote the London Needs You Alive Campaign within local prevention awarness campaigns
| 4 | Serious Youth Violence an agenda item at local DCS/Headteacher fora at least annually
| 5 | Promotion of membership of youth organisations e.g. Volunteer Police Cadet Scheme, London Fire Brigade Cadet Scheme, Scouts local voluntary sector organisations
| 6 | Supporting the transition from Primary to Secondary School, through programmes that introduce year 6 pupils to their new school and provide mentoring and pastoral support (e.g. Stepping Stones)
| 7 | Support key transition stages in a young person life that can increase their vulnerability (changing schools, returning to education from young offenders institution; leaving care)
| 8 | Make Premier League Kickz Programme available to PRUs (in those boroughs where the programme operates)
| 9 | Adoption of a restorative justice approach
| 10 | Demonstrable consideration by safeguarding and the community safety partnership of parental engagement approach; active strategies for engagement, including socio-education offer, across key partners, especially within schools, PRUs and colleges.
| 11 | Recognising the key role of parents and carers, and the extensive evidence on benefits of parental support and education, clear socio-education offer on local risks and themes relating to youth violence (in particular, grooming, exploitation and healthy relationships) as part of an effective prevention offer for young people
| 12 | Support work to promote healthy relationships to help address gender based violence in schools (e.g. VRU Tender programme)
| 13 | Equalities impact of programmes implemented are assessed and considered to ensure diverse needs of young people, families and communities are responded to contextually, with potential negative impact fully understood.
| 14 | A clear partnership response to identifying, assessing and responding to extra-familial harm is documented within a safeguarding partnership strategy; tools to effectively deliver the strategy are available to practitioners and professionals as recommended by Ofsted.
| 15 | Structural issues which contribute to disproportionalities within violence, service access and school exclusions are understood by the partnership, and clear action to address are outlined within key strategic departments and multi-agency plans, as well as public sector equality planning.
| 16 | Local safeguarding partnerships coordinate efforts to ensure local Early Help processes and referral pathways, and everyone's role within them, are clear and easily accessible to parents/carers, schools, PRUs and college staff.
| 17 | Adoption/promotion of initiatives (such as a school watch) to promote safe journeys to/from school for children and young people.
| 18 | Deliver Safety First Blue Light Collaboration (LAS and LFB) to year 8 students in schools covering topics of serious youth violence, CSE and Sexting.
WORKING WITH COMMUNITIES AND NEIGHBOURHOODS TO REDUCE VIOLENCE | 1 | Map key communities and leaders, review six monthly.
| 2 | Consider use of the Business Community Safety Toolkit, to support sharing of good practice between businesses in preparing for or responding to an incident of violence https://www.london.gov.uk/sites/default/files/business_community_safety_toolkit_b.pdf
| 3 | Implement hyper-local neighbourhood initiatives to support community cohesion in areas at high risk of violence. Co-produce with the community, projects within the neighbourhood designed to improve communication with and trust in statutory services, support for young people through mentoring, training and positive activities, enhance the physical layout and take opportunities to design out crime.
| 4 | Promote Fearless as a crime information source and option for providing information about violence anonymously https://www.fearless.org/en
| 5 | Develop a communications plan which engages communities in the programme, and supports a reduction in fear of crime through providing honest and positive messages about achievements and reduces risk of stigma and discrimination.
| 6 | Involve young people within local violence prevention work, through both established forums such as youth councils/parliaments, youth Independent Advisoy Groups and informal grassroots pathways including through social media platforms.
| 7 | Work with communities and other partners in hyper local areas to develop capacity building to support incident response in the community, through robust partnership approach, and to increase trust and collaboration between local communities, stakeholders, key local institutions, and statutory partners. (e.g VRU My Ends, VRU Capacity building programme)
| 8 | With partners initiate a parents network that communicates on a regular basis to disseminate information about problems/ issues in the borough, to consult with them about contemporary parenting challenges and possible solutions and to ensure no-one feels alone in confronting these challenges.
| 9 | Police to work with local communities at a ward level, governed by ward panels, with the introduction of a new mandatory ward panel priority that must focus on violence or drivers of violence.
SUPPORTING VICTIMS OF VIOLENCE AND VULNERABILITY Ensuring co-ordinated referral and support to victims and those who are vulnerable | 1 | Agree a common Youth Violence risk assessment and management framework. Consult and agree on a best practice based, borough wide, youth violence risk assessment and management framework. Having established a framework disseminate and embed in council and partner practices and processes through training and briefing.
| 2 | Provide front line staff within partner agencies with trauma and attachment training,in order to support practitioners working with young people to understand the ‘Trauma Informed Approach’. This approach informs staff of how trauma in early life may affect current behaviour.
| 3 | Ensure there is a robust mechanism to identify and manage any risk when young people move to different areas by including effective handover between agencies.
POSITIVE DIVERSION FROM VIOLENCE Recognising that young people should be offered interventions which help them move away from criminality | 1 | Young offenders to have RO/YRO conditions/requirements tailored to the nature of the violence offending and service provision available locally through the YOT. Reference https://www.london.gov.uk/sites/default/files/brave_space_-_knife_crime_toolkit_1.pdf
| 2 | Work with the Voluntary Community Sector to develop and deliver a range of services that support young people and enhance the overall approach to tackling serious youth violence
| 3 | Partnership support for Police applications for post-conviction Criminal Behaviour Orders (CBO's) for repeat knife offedners, in order to create better levers for change, by including positive requirements in sentences and orders to support the opportunity for change.
| 4 | Using the ASB early intervention scheme to deal with people involved in ASB, potentially preventing future criminal behaviour, responding to offending behaviour, increasing intelligence, highlighting safeguarding issues and providing opportunities prior to any enforcement .
| 5 | Co-ordination between Probation and other partners to ensure robust pre-release plans, in order to provide support for a positive transition from secured estate back into the community.